## Slide 1
ASSIGNMENT II – PART 2
College Event Planning & Review
TECH NOVA 2027
5th Annual National Technical Symposium
Feb 14-15, 2027
Sri Sairam Engineering College, Chennai
Arjun V B | 711523BCB009
A National-Level Technical Fest
Covering: Goal Audience Timeline Budget Promotion Approvals Roles Recording Post-Event Review
800+
Participants
Rs.2.45L
Total Budget
Rs.42k
Prize Pool
8
Events
Code Sprint
Rs.5k
Paper Presentation
Rs.4k
Project Expo
Rs.6k
Hackathon 24hr
Rs.15k
Tech Quiz
Rs.3k
Web Design
Rs.4k
Debugging
Rs.2k
Circuit Design
Rs.3k
40+ Colleges
Participating
50 Volunteers
Deployed
2 Days
of Competition

## Slide 2
2 / 5 | GOAL AUDIENCE TIMING PREPARATION
Goal, Audience & 8-Week Preparation Timeline
PRIMARY GOAL
Bridge academia and industry. Provide 800+ students from 40+ colleges a platform to compete, collaborate and connect with industry professionals through 8 technical events across 2 days.
AUDIENCE BREAKDOWN
External Students (40+ colleges)
600
Internal Students
200
Industry Judges
15
Faculty & Chief Guests
50
TOTAL
865
8-WEEK PREPARATION TIMELINE
Dec 21
Form committee, assign coordinators, create comms groups
Jan 4
Submit Principal/HOD approval + launch social media + open registration portal
Jan 11
Sponsors confirmed + registration opens + chief guest invited
Jan 25
Registration closes + participant list finalized + print ID cards
Feb 7
3-hr volunteer orientation + venue walkthrough + full dry run
Feb 13
Full venue setup + banners + AV/lab tech check
Feb 14-15
EVENT DAYS Inauguration All 8 Events Cultural Evening Valedictory
Feb 22
Post-event review + certificates emailed + event report to HOD

## Slide 3
3 / 5 | BUDGET RESOURCES PROMOTION APPROVALS
Budget, Resources & Promotion Strategy
Rs.2,45,000
Total Income
Rs.1,97,250
Expenditure
Rs.47,750
Net Surplus
Rs.42,000
Prize Pool
EXPENDITURE BREAKDOWN
Prizes Trophies Certificates
Rs.55,000
Food Hospitality (2 days)
Rs.48,000
Technical Equipment Rental
Rs.22,000
Printing Branding
Rs.18,000
Stage Decor Lighting
Rs.15,000
Photography Video
Rs.12,000
Guest Hospitality
Rs.10,000
Contingency 5pct
Rs.12,250
INCOME SOURCES
Registration Fees (800 x Rs.150)
Rs.1,20,000
Title Sponsor
Rs.50,000
Co-Sponsors (2 x Rs.15k)
Rs.30,000
College Management Grant
Rs.40,000
Exhibition Stall Fees
Rs.5,000
PROMOTION CHANNELS
Instagram
Daily reels countdowns events
WhatsApp
Broadcast to 40+ college reps
Unstop
External registration listing
Email
Outreach to 40 HODs coordinators
Physical Posters
5 nearby engineering colleges
APPROVAL CHAIN
Student Event Head --> Dept. Faculty Coordinator --> HOD --> Vice Principal --> Principal --> Management (>Rs.1L)

## Slide 4
4 / 5 | APPROVALS EVENT-DAY ROLES VOLUNTEER DEPLOYMENT
Event-Day Roles & Volunteer Operations
CORE COMMITTEE (9 ROLES)
Event Head
Overall coordination, crisis management, final decisions
Deputy Head
Logistics, vendor payments, equipment issues
Finance
Cash management, sponsor liaison, expense tracking
Registration
Check-in, ID cards, attendance, participant data
Technical
AV setup, Wi-Fi, lab systems, backup plans
Hospitality
Food arrangement, guest reception, VIP transport
Stage and MC
Programme anchoring, ceremonies, timing
Publicity
Photos, video direction, live social media reels
Volunteer Head
Manages all 50 volunteers across 8 stations
VOLUNTEER DEPLOYMENT (50 total)
Main Gate & Entry
5 volunteers
ID check, crowd control
Registration Desk
8 volunteers
Participant check-in, kit distribution
Seminar Halls A & B
6 volunteers
Seating, announcements, judge help
Computer Labs
8 volunteers
Monitor participants, technical help
Exhibition Hall
6 volunteers
Project expo setup and supervision
Auditorium
6 volunteers
Ushering, stage assistance, seating
Food Area
5 volunteers
Food distribution, queue management
Roving Volunteers
6 volunteers
General help, message running

## Slide 5
5 / 5 | RECORDING POST-EVENT REVIEW LESSONS REFLECTION
Documentation, Review & Key Learnings
RECORDING PLAN
Inauguration & Valedictory
Professional videographer hired
All event sessions
3 assigned volunteer photographers
Hackathon progress
Time-lapse + periodic photos every hour
Attendance
Physical sign-in + Google Form QR at entry
Participant feedback
Exit gate QR satisfaction survey
Financial records
Real-time expense log by finance coordinator
POST-EVENT SUCCESS METRICS
Overall Satisfaction Score
4.0 / 5.0 minimum
Registration to Attendance
80% conversion rate
Event Start Delay
15 minutes maximum
Technical Incidents
3 incidents maximum
Social Media Reach
10,000+ impressions
Budget Adherence
Within 5% of plan
LESSONS FROM TECHNOVA 2026
Registration bottleneck
200 in 30 min -- assign arrival time slots
Wi-Fi failed in coding
Dedicated LAN for labs -- no shared Wi-Fi
Lunch 45 min late
Pre-order 3 days ahead + stagger lunch halls
12 certificate errors
Participant self-verify portal 1 week before
Only 3k social reach
Dedicated reels volunteer + post every 2 hours
STUDENT REFLECTION
"Communication gaps cause 80% of event-day problems. Having organized TechNova 2026, the biggest issue was that volunteer briefing happened 30 minutes before opening -- nobody knew their station. For TechNova 2027 I would enforce a 3-hour orientation one week before, a broadcast-only WhatsApp group for day-of updates, and a 15-minute morning muster before anything opens. The best part is watching 800 strangers walk in, compete, make friends, and leave with something they could not find in a classroom."
-- Arjun V B, 711523BCB009